## Project Summary
Budget Proposal
Texas Conference of Urban Counties
Participating Member County : | Collin County |  |  |  | Software Licenses |  |  | License Fee
CUC Enterprise License
Budget Proposal Date: | 2008-12-12 |  |  |  | Case Management
[5 empty] | Probate & Mental Health | No | Included In CUC Enterprise License
Tyler Technologies Contact: | John Galbraith |  |  |  | Civil & Family | No
| Account Manager |  |  |  | Criminal | No
| Tyler Technologies |  |  |  | Justice of the Peace | No
| 6500 International Parkway, Suite 2000 |  |  |  | Prosecutor | No
Plano, Texas 75093
| 972/713-3770 |  |  |  | Additional Products - County License
| John.Galbraith@TylerTechnologies.com |  |  |  | Jail Management | Yes |  | 375000
[5 empty] | Law Enforcement/RMS | Yes |  | Included
[5 empty] | Community Supervision | No |  | 0
Major Assumptions |  |  |  |  | Hot Checks | No
*See Assumptions Detail for more information
[5 empty] | Total - Local County Licenses |  |  | 375000
Expected Project Manager Duration
CUC Enterprise Products: | 0 | Months
Additional Products: | 18 | Months |  |  | Implementation Services |  | Hours | Cost
Total: | 18 | Months |  |  | Summary
[5 empty] | Project Management |  | 3681 | 588960
Project Management dedication: | 90% |  |  |  | Implementation Plan |  | 256 | 40960
[5 empty] | Fit Analysis |  | 384 | 57216
Number of Standard Interfaces: | 8 |  |  |  | Data Conversion |  | 760 | 113240
[5 empty] | Interfaces |  | 1335 | 198915
Data Conversion Approach: | Approach 3 - Client to perform data conversion with Tyler assistance |  |  |  | Customization |  | 3665 | 546085
[5 empty] | Configuration & Consulting |  | 800 | 119200
[5 empty] | Training |  | 560 | 77280
Training Approach: | Tyler to perform direct training to end-users |  |  |  | Go-Live Assistance |  | 640 | 88320
| Collin will perform training for Inquiry Users |  |  |  | Other Services |  | 870 | 129630
Travel Allowance Assumptions | 3.5 | days/trip. | 663.1187 | est. days onsite.
|  |  | 189.4625 | est. trips. | Services Totals |  | 12951 | 1959806
Overnight hotel required? | Yes
Air travel required? | Yes |  |  |  | Travel Allowance Budget |  |  | 26908.5625
[5 empty] | Total Software License & Implementation Services |  |  | 2361714.5625
Selected:
Approach 3 - Client to perform data conversion with Tyler assistance
Data Conversion Approaches
Approach 1 - Standard conversion of TSG UNIX products
Approach 2 - Standard data conversion by Tyler analysts
Approach 3 - Client to perform data conversion with Tyler assistance
Yes
No

## Services Detail
Services Detail
Collin County
| Rate | Hours | Cost |  | Rate | Hours | Cost
CUC Products |  |  |  | Additional Products
Project Management | 160 |  | 0 | Project Management | 160 | 3681 | 588960 | 801 | PE - 25% for 18 months
Implementation Plan | 160 | 256 | 40960 |  |  |  | 0
Customization | 149 |  | 0 | Customization | 149 | 3665 | 546085
Courts
Probate & Mental Health (CC) |  |  | Not In Scope | Jail Management |  |  | In Scope
Fit Analysis | 149 | 0 | 0 | Fit Analysis | 149 | 304 | 45296
Data Conversion | 149 | 0 | 0 | Data Conversion | 149 | 600 | 89400
Interfaces | 149 | 0 | 0 | Interfaces | 149 | 1335 | 198915
Configuration & Consulting | 149 | 0 | 0 | Configuration & Consulting | 149 | 640 | 95360
Training | 138 | 0 | 0 | Training | 138 | 480 | 66240
Go-Live Assistance | 138 | 0 | 0 | Go-Live Assistance | 138 | 480 | 66240
Civil & Family (CC & DC) |  |  | Not In Scope | Law Enforcement / RMS |  |  | In Scope
Fit Analysis | 149 | 0 | 0 | Fit Analysis | 149 | 80 | 11920
Data Conversion | 149 | 0 | 0 | Data Conversion | 149 | 160 | 23840
Interfaces | 149 | 0 | 0 | Interfaces | 149 | 0 | 0
Configuration & Consulting | 149 | 0 | 0 | Configuration & Consulting | 149 | 160 | 23840
Training | 138 | 0 | 0 | Training | 138 | 80 | 11040
Go-Live Assistance | 138 | 0 | 0 | Go-Live Assistance | 138 | 160 | 22080
Criminal (CC & DC) |  |  | Not In Scope | Probation |  |  | Not In Scope
Fit Analysis | 149 | 0 | 0 | Fit Analysis | 149 | 0 | 0
Data Conversion | 149 | 0 | 0 | Data Conversion | 149 | 0 | 0
Interfaces | 149 | 0 | 0 | Interfaces | 149 | 0 | 0
Configuration & Consulting | 149 | 0 | 0 | Configuration & Consulting | 149 | 0 | 0
Training | 138 | 0 | 0 | Training | 138 | 0 | 0
Go-Live Assistance | 138 | 0 | 0 | Go-Live Assistance | 138 | 0 | 0
Justice of the Peace |  |  | Not In Scope | Hot Checks |  |  | Not In Scope
Fit Analysis | 149 | 0 | 0 | Fit Analysis | 149 | 0 | 0
Data Conversion | 149 | 0 | 0 | Data Conversion | 149 | 0 | 0
Interfaces | 149 | 0 | 0 | Interfaces | 149 | 0 | 0
Configuration & Consulting | 149 | 0 | 0 | Configuration & Consulting | 149 | 0 | 0
Training | 138 | 0 | 0 | Training | 138 |  | 0
Go-Live Assistance | 138 | 0 | 0 | Go-Live Assistance | 138 |  | 0
Prosecutor |  |  | Not In Scope | Other/Additional Services
Fit Analysis | 149 | 0 | 0 | Evening/Off Hours Go-Live Assistance | 175 | 150 | 22350
Data Conversion | 149 | 0 | 0 | ICJ Coordinator | 149 | 720 | 107280
Interfaces | 149 | 0 | 0 |  |  |  | 0
Configuration & Consulting | 149 | 0 | 0 |  |  |  | 0
Training | 138 | 0 | 0 |  |  |  | 0
Go-Live Assistance | 138 | 0 | 0 |  |  |  | 0
0
Total Services - CUC Products |  | 256 | 40960 | Total Services - Additional Products |  | 12695 | 1918846
Project Management |  | 0 | 0 | Project Management |  | 3681 | 588960
Implementation Plan |  | 256 | 40960 | Implementation Plan |  | 0 | 0
Fit Analysis |  | 0 | 0 | Fit Analysis |  | 384 | 79566
Data Conversion |  | 0 | 0 | Data Conversion |  | 760 | 220520
Interfaces |  | 0 | 0 | Interfaces |  | 1335 | 198915
Customization |  | 0 | 0 | Customization |  | 3665 | 546085
Configuration & Consulting |  | 0 | 0 | Configuration & Consulting |  | 800 | 119200
Training |  | 0 | 0 | Training |  | 560 | 77280
Go-Live Assistance |  | 0 | 0 | Go-Live Assistance |  | 640 | 88320
|  |  |  | Other Services |  | 870 | 129630
Note on C6: : Implementation Planning + 80 hours "advanced" demo/follow-up
Note on G15: : 8am to 5pm
Note on G21: : 1 Trainer for 2 weeks
Note on G38: : Evenings and weekends
Note on I5: : 15 months PM + 25% of 15 months for PE
Note on I10: : Integration is 3 people for 1 week and regular fit is 2 people for 1 week plus 80 hours estimating sessions. Add'l time for DBA consulting regarding conversion/blending converted jail data with existing Odyssey data.
Note on I13: : Include API consulting here
Note on I14: : 120 users / 20 seats = 6 sessions 2 Trainers for 3 weeks
Note on I15: : 4 people for 3 weeks
Note on I18: kevin.watson: Added consulting time after meeting with the client on 12/22/08. They stated there would be a conversion.
Note on I38: : 1.25 people for 3 weeks

## Assumptions Detail
Assumptions Detail
Collin County
Project Management
1) | Project manager will be dedicated to client project for |  |  |  |  | 90% | of
| 18 | month project duration, or up to |  |  | 3681 | hours.
2) | The Tyler project manager will be on-site as needed during the course of the project,
however some percentage of the Tyler project manager's time will be spent coordinating
Tyler resources and projects at Tyler's Plano, Texas offices. For travel expense estimation
| purposes, Tyler has assumed |  |  | 70% | on-site project manager presence.
3) | Client will designate a full-time project manager who will serve as Tyler's primary
contact
Implementation Plan
1) | In accordance with Sections 1.24 and 2.2 of the Master Software License and Professional
Services Agreement, Tyler will prepare an Implementation Plan at the Participating Member
County's expense, which will then be subject to a Notice to Proceed or Notice to Cancel by
the Participating Member County.
Decision must be made within 2 weeks from delivery of the implementation plan to the county
2) | 256 | hours plus any required travel expenses is allocated for the development of the
Implementation Plan.
Fit Analysis
1) | At the beginning of each project phase, a fit analysis will be conducted onsite to refine
the list of development tasks required to install the case types or modules included in
that phase.
Data Conversion
1) | Tyler has consulted with the County's technical staff to select a conversion approach from
one of three options, each of which are described below.
2) | Conversion for Law Enforcement Civil Papers is required. Follow up from 12/22/08 meeting
3) | The conversion approach for this project is:
Approach 3 - Client to perform data conversion with Tyler assistance
| APPROACH 1 |  |  |  | APPROACH 3
| A) Tyler will perform a standard conversion from the |  |  |  | A) Tyler will deliver to the Participating Member County
| Participating Member County's existing TSG software. |  |  |  | a copy of Tyler's IFL Conversion Tool, which will include
| B) This proposal assumes that data will be converted |  |  |  | a schema, data documentation, and various data
| "as-is" with limited or zero data manipulation or |  |  |  | validation and verification programs.
| cleanup. |  |  |  | B) Tyler will provide training on the use of the IFL
| APPROACH 2 |  |  |  | Conversion Tool to Participating Member County's
| A) The Participating Member County will provide Tyler |  |  |  | technical staff.
| with data from the source system(s) in a non-proprietary |  |  |  | C) Tyler assumes that County's technical staff is
| format (e.g. SQL Server tables, comma separated ASCII |  |  |  | already proficient in the Microsoft SQL Server database.
| files, or some other mutually agreeable form, and on |  |  |  | D) County technical staff will then export data from the
| media that is readble by Tyler. |  |  |  | surce system into the IFL Conversion Tool, at County
| B) Tyler will perform a standard conversion from the |  |  |  | expense, with consulting assistance from Tyler.
| source system(s) to the Odyssey database using Tyler's |  |  |  | E) Tyler will assist the County in loading data from
| existing IFL Conversion Tool. |  |  |  | the IFL Conversion Tool into the Odyssey production
| C) This proposal assumes that data will be converted |  |  |  | database.
"as-is" with limited or zero data manipulation or cleanup.
Interfaces
1) | At the time of this proposal, Tyler has reviewed only limited or high-level information
regarding the Participating Member County's requirements for interfaces to other systems.
2) | The Participating Member County will utilize Tyler Integration Tools
for in-house development of interfaces to other systems.
3) | Tyler will provide consulting assistance on a T&M basis for the Participating Member County's
in-house development of integrations utilizing Tyler Integration Tools.
4) | Participating Member County must pay license fees for Tyler Integration Tools prior to their use.
5) | Purchase of license for integration tools will be handled outside of this proposal.
6) | Budget for interfaces may be used either for T&M services or for additional Tyler Integration Tools
to address business requirements.
Customization
1) | This proposal includes up to |  |  | 3665 | hours of services for the development of any
local software modifications.
2) | At the time of this proposal, the specific local modifications, if any, desired by the Participating
Member County are not known or are not fully documented by Tyler and the County. Each
customization project must be individually estimated by Tyler, and approved by the Participating
Member County, prior to the beginning of any work on that customization.
Configuration & Consulting
1) | This proposal includes up to |  |  | 800 | hours of assistance by Tyler analysts and trainers
to assist the Participating Member County with the configuration of the system which includes
defining security priviledges, setting up code tables, and defining system behavior and business
rules.
2) | Configuration & Consulting hours may also be used, upon joint agreement of Tyler and the
Participating Member County, for Tyler business or technical analysis services desired by the
County.
Training
1) | This training proposal includes |  |  | 560 | hours for training of the Participanting Member
County's employees by Tyler training personnel.
2) | The Participating Member County will provide a facility and equipment sufficient that training
participants can each have hands-on access to a computer workstation during training.
3) | Training classes will have no more than 20 training participants per instructor.
4) | Additional training for non-employee users (e.g. criminal justice business partners who the
County may wish to provide access) can be provided through a train-the-trainer approach
with County employees conducting the training.
Go-Live Assistance
1) | This proposal includes up to |  |  | 640 | hours of onsite 8am - 5pm business hours assistance
subsequent to go-live activities.
2) | This proposal includes up to |  |  | 150 | hours of onsite 5pm - 8am non-business hours
assistance subsequent to go-live activities.
Servers, Workstations, and Third Party Software
1) | The Participating Member County will provide servers, workstations, and peripheral equipment
that conform to the specifications and requirements provided by Tyler to the CUC.
2) | Server operating system, database licenses, and any other Third Party Software specified
in the Master Software License and Professional Services Agreement will be provided by
The Participating Member County.
Collin to provide current and future technology specifications to validate hardware fit
Other Notes and Assumptions
Travel Allowance
1) | Actual travel expenses will be billed based on the CUC's Administrative policy on travel.
2) | For this project, the following travel requirements exist:
| a) | Overnight hotel lodging for local Tyler employees is NOT required, however, for non-local Tyler employees IS required.
| b) | Airline Travel to client site for local Tyler employees is NOT required, however, for non-local Tyler employees IS required.
3) | Travel is based on average estimated daily expenses as follows:
| 12 | Meals/day |  | 18 | Auto mileage or rental car/day & parking
| 90 | Lodging/day |  | 250 | Per roundtrip airline ticket.
4) | Based on the percent travel assumptions refelcted below, Tyler estimates approximately
| 663.1187 | days onsite during the course of the project.
5) | For the purposes of calculating potential airline expenses, Tyler estimates that the average site
| visit duration will be |  | 3.5 | days per trip, for a total count of |  |  | 189.4625 | trips.
6) | Activites are estimated as follows for percent requiring travel to client site:
|  |  | Local Tyler Employees |  |  |  |  | Non-Local Tyler Employees
|  |  |  | Daily Est. Expenses: | 12 | 90 | 18 |  | Daily Est. Expenses: | 12 | 90 | 18
|  | Travel Assumptions | %Onsite | # Days | Meals | Hotel | Auto | %Onsite | # Days | Meals | Hotel | Auto
|  | Project Management | 70% | 322.0875 | 3865.05 | 0 | 5797.575 | 0% | 0 | 0 | 0 | 0
|  | Implementation Plan | 70% | 22.4 | 268.8 | 0 | 403.2 | 10% | 3.2 | 38.4 | 288 | 57.6
|  | Fit Analysis | 70% | 33.6 | 403.2 | 0 | 604.8 | 10% | 4.8 | 57.6 | 432 | 86.4
|  | Data Conversion | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
|  | Interfaces | 0% | 0 | 0 | 0 | 0 | 12% | 20.025 | 240.3 | 1802.25 | 360.45
|  | Customization | 5% | 22.9062 | 274.875 | 0 | 412.3125 | 0% | 0 | 0 | 0 | 0
|  | Configuration & Consulting | 50% | 50 | 600 | 0 | 900 | 0% | 0 | 0 | 0 | 0
|  | Training | 80% | 56 | 672 | 0 | 1008 | 0% | 0 | 0 | 0 | 0
|  | Go-Live Assistance | 100% | 80 | 960 | 0 | 1440 | 12% | 9.6 | 115.2 | 864 | 172.8
|  | Other Servies | 70% | 76.125 | 913.5 | 0 | 1370.25 | 0% | 0 | 0 | 0 | 0
[5 empty] | 7957.425 | 0 | 11936.1375 |  |  | 451.5 | 3386.25 | 677.25
[5 empty] | Local Subtotal |  | 19893.5625 |  |  | Non-Local Subtotal |  | 4515
[7 empty] | Airline trips: | 10 |  | Subtotal Airline |  | 2500
[7 empty] | Average roundtrip ticket price: | 250 |  | Total Travel |  | 26908.5625

## General Assumptions
General Assumption Detail
General Assumptions
1 | Notice of Decision to proceed must be signed by March 31, 2009 to make the September release (2009 SP2)
2 | Law Enforcement Go-Live #1 will not include any modifications.
3 | Law Enforcement modifications are currently estimated at 50 hours and will be implemented during Law Enforcement Go-Live #2.
4 | Law Enforcement Go-Live #1 will include Constable Precinct 1 only. Law Enforcement Go-Live #2 will include remaining Constable precincts and the Sherriff's Office.
5 | Jail Modifications and Integrations required for go-live are At Risk of exceeding the number of available hours for the Release of Odyssey available in the desired project timeline. Jail Modifications required for go-live need to be reviewed and prioritized by Collin County to determine highest to lowest priority modifications for Go-Live. In the event certain Go-Live modifications cannot be delivered in the targeted Go-Live Release, best effort will be made to follow the priority of modifications determined by Collin County. Where feasible, Tyler will deliver required modifications post-release as a Patch Update prior to Go-Live.
6 | Release Delivery dates are estimated on good faith and may change depending on overall complexity of the release.
7 | Jail Modifications identified as "Future Requirements" will be delivered after go-live in a Release to be determined later.
8 | Modifications and Interfaces listed under "Not Estimated" are Not In Scope for this proposal.
9 | Jail Integration Toolkit License fee will be waived, but overall annual maintenance will increase by $10,000 per year
10 | LE will include conversion. Collin will perform the conversion activities and Tyler will provide consulting.
11 | Criminal and Prosecutor timeline will need to move out to align with Jail Go-Live

## Mod Detail
Modifications Detail
Collin County Modifications - Estimated
Product Area | Source | Priority | Description | Notes | Hours | Range | Current Contract Hours | New Contract Hours
Case Manager | Business Review | 1 | Enhance Cash Bond Receipting | Go-Live | 150 | 120-200 | 49.5 | 100.5
Jail Manager | Demo | 1 | Inmate Tracking for Escort Free Movement Alerts | Go-Live | 375 | 301-450 | 130 | 245
Jail Manager | Demo | 1 | Mentalix Livescan Interface Adjustments | Go-Live | 110 | 55-140 | 40 | 70
Jail Manager | Demo | 1 | Inmate "Keep Away" Processing | Go-Live | 575 | 451-700 | 200 | 375
Jail Manager | Business Review | 1 | "Smart Packets" Design form to contain the information - Assume 10 Tokens | Go-Live | 160 | 160-220 | 55 | 105
Jail Manager | Business Review | 1 | Show family members address on the releationship list | Go-Live | 100 | 40-120 | 33 | 67
Jail Manager | Business Review | 1 | New Report - Jail Roster including Jail Flags | Go-Live | 85 | 70-90 | 30 | 55
Jail Manager | Business Review | 1 | Print Offense Description on Bond Receipt | Go-Live | 140 | 115-170 | 46.2 | 93.8
Law Enforcement | Business Review | 1 | Show which office issued the civil paper on the search screen | Go-Live | 50 | 40-60 | 16.5 | 33.5
|  |  |  | Sub-Total | 1745 |  | 600.2 | 1144.8
Jail Manager | Demo | 3 | Internal Jail Incident Report Approval Process | Future | 375 | 301-450 | 0 | 375
Jail Manager | Demo | 3 | Decision Tree Classification Development ** | Future | 375 | 301-450 | 0 | 375
Jail Manager | Business Review | 3 | Place inmate property into bin/bag prior to booking | Future | 320 | 256-400 | 0 | 320
Jail Manager | Business Review | 3 | Add collection of family information to booking checklist | Future | 100 | 55-140 | 0 | 100
Jail Manager | Business Review | 3 | Cell Recommendation Based on Classification | Future | 155 | 130-180 | 0 | 155
Public Access | Demo | 3 | Scanned Document Watermark for Printing | Future | 220 | 141-300 | 0 | 220
Public Access | Demo | 3 | Collin GIS Database/Maps Interface for Web Lookup Plotting on Public Access | Future | 375 | 301-450 | 0 | 375
|  |  |  | Sub-Total | 1920 |  | 0 | 1920
** Decision Tree intellectual property must be licensed from NorthPointe, Inc.
prior to Tyler beginning any development efforts. The cost of this license fee
is unknown at this time and must be paid by Participating Member County.
|  |  |  | Grand Total | 3665 |  | 600.2 | 3064.8
Collin County Modifications - Not Estimated At This Time
Product Area | Source | Priority | Description | Notes | Hours | Range | Current Contract Hours | New Contract Hours
Jail Manager | Business Review |  | Query Bond Company by ID / Assign Sequentially by System | Review in Fit Analysis
Law Enforcement | Business Review |  | Allow Civil Paper Search by Address | Need Clarification
Law Enforcement | Business Review |  | Initiate Civil Paper Intake by "Copy Function" | Need Clarification

## Integration Detail
Integration Detail
Collin County Integrations - Estimated
Product Area | Source | Priority | Description | Notes | Hours | Range | Current Contract Hours | New Contract Hours
Jail Manager | Product Owner | 1 | Adding Outbound Publishing to Odyssey Jail Manager Integration Toolkit | Go-Live | 450 | 301-450 |  | 450
Jail Manager | Questionnaire | 1 | Sending Mugshots to ICS RMS | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Sending Jail Data to jailseach.com | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Sending Jail Data to AutoPin | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Sending Jail Data to TouchPay Kiosk System | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Sending Jail Data to NaphCare (CHM & COEMR) Inmate Medical | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Sending Jail Data to Vertex | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Sending Jail Data to CC HLS | Go-Live | 80 | 60-80 |  | 80
Jail Manager | Questionnaire | 1 | Receiving Data from City of Plano Police Dept. | Go-Live | 225 | 141-300 | 225
Jail Manager | Questionnaire | 1 | Sending Jail Data to LoneStar/Tiger Commissary System | Go-Live | 100 | 55-140 | 100
|  |  |  | Grand Total | 1335 |  | 325 | 1010
Collin County Integrations - Not Estimated At This Time
Product Area | Source | Priority | Description | Notes | Hours | Range | Current Contract Hours | New Contract Hours
Jail Manager | Questionnaire |  | AFIS | Is this Needed?

## Estimated Timeline
Collin County - Estimated Project Timeline
2Q 2008 |  |  | 3Q2008 |  |  | 4Q 2008 |  |  | 1Q 2009 |  |  | 2Q 2009 |  |  | 3Q 2009 |  |  | 4Q 2009 |  |  | 1Q 2010 |  |  | 2Q 2010 |  |  | 3Q 2010 |  |  | 4Q 2010 |  |  | 1Q 2011 |  |  | 2Q 2011 |  |  | 3Q 2011 |  |  | 4Q 2011
A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F
Develop Sonant Mods
|  |  |  | Justice of the Peace | [8 empty] | GL JP (1) |  |  | GL JP (4)
Develop LE Mods
[10 empty] | Imp Plan |  | LE |  |  |  | GL #1 |  |  | GL #2
[12 empty] | Develop Go-Live Jail Mods | [5 empty] | Develop post Go-Live Jail Mods | [5 empty] | Develop Jail Mods
[10 empty] | Imp Plan |  | Jail | [8 empty] | GL |  | Jail - Post Go-Live
| Criminal & Prosecutor | [19 empty] | GL
7 | 8 | 9 | Months |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
Legend
|  |  |  | = | Primary Release (estimated)
|  |  | X | = | Primary Release to be used for go-live in Phase X (estimated)
|  |  |  | = | Secondary Release
|  |  |  | = | One of the major phases
|  |  |  | = | Implementation Planning phase