COLLIN COUNTY

PURCHASING DEPARTMENT

CHANGE ORDER NO:  12

CONTRACT:		Construction, Building:  Collin County Administration Building

CONTRACT NO.  	05097-07

CHANGE ORDER ISSUED TO:

RATCLIFF CONSTRUCTORS, L.P.

Attn: Scott Graham

14901 Quorum Dr., Ste 715

Dallas, Texas 75254

AWARDED BY:  Original Court Order No.		2007-943-10-23 and modified by 2007-1068-11-27

CHANGE ORDER #1, COURT ORDER NO. 	2008-254-04-15

CHANGE ORDER #2, COURT ORDER NO._____  2008-297-04-29____________________________________________

CHANGE ORDER #3, COURT ORDER NO.______2008-378-06-03____________________________________________

CHANGE ORDER #4, COURT ORDER NO.______FYI______________________________________________________

CHANGE ORDER #5, COURT ORDER NO.______FYI______________________________________________________

CHANGE ORDER #6, COURT ORDER NO.______2008-706-09-09____________________________________________

CHANGE ORDER #7, COURT ORDER NO.______FYI______________________________________________________ CHANGE ORDER #8, COURT ORDER NO.______2008-1099-12-09___________________________________________

CHANGE ORDER #9, COURT ORDER NO.______FYI		___________________________________________

CHANGE ORDER #10, COURT ORDER NO._____	2009-094-02-02	___________________________________________

CHANGE ORDER #11, COURT ORDER NO._____	FYI		___________________________________________

CHANGE ORDER #11, COURT ORDER NO._____	FYI		___________________________________________

YOU ARE DIRECTED TO MAKE THE FOLLOWING CHANGE TO THIS CONTRACT:

PCO# 63,	Additional Work Required by the McKinney Fire Marshal………………………………..$ +    6,117.10

PCO# 67,	Elevator Room Ceiling……………………………………………………………………..$ +    4,305.26

PCO# 68,	Sprinkler Relocate in Penthouse……………………………………………………………$ +    1,669.93

PCO# 64,	Penthouse Access…………………………………………………………………………...$ +    7,409.60

ADD: Five (5) Calendar Days to Contract.  New Contract Delivery Date is 2/24/09.

Total for Change Order No. 12  …………………………………………………………...............................$ +  19,501.89

Except as provided herein, all terms and conditions of the contract remain in full force and effect and may only be modified in writing signed by both parties.

The original (contract sum) was	$ 16,798,250.00

Net Change to Change Order(s) (show $ plus, minus or unchanged)

PREVIOUS Change Order No.      1       $  + 145,517.01

PREVIOUS Change Order No.      2       $  +   55,151.80

PREVIOUS Change Order No.      3	     $  -     9,747.52

PREVIOUS Change Order No.      4       $  +   21,414.80_______

PREVIOUS Change Order No.      5       $  -    28,296.50_______

PREVIOUS Change Order No.      6       $  -    22,718.00_______

PREVIOUS Change Order No.      7       $  +   32,875.07_______

PREVIOUS Change Order No.      8       $  -  833,007.50________

PREVIOUS Change Order No.      9       $  +   33,172.80________

PREVIOUS Change Order No.     10      $  +   15,528.30________

PREVIOUS Change Order No.     11      $  +   36,432.00________

CURRENT  Change Order No.     12      $  +   19,501.89________

TOTAL CHANGE ORDERS TO DATE: 	$     -534,175.85

The new (contract sum) including this Changer Order will be 	$  16,264,074.15

ACCEPTED BY:							ACCEPTED AND AUTHORIZED BY

AUTHORITY OF COLLIN COUNTY

Ratcliff Constructors, L.P.					COMMISSIONERS’ COURT

CONTRACTOR/ENGINEER

ADDRESS 							Collin County Courthouse

14901 Quorum Dr.						210 S. McDonald

Ste 715								McKinney, Texas  75069

Dallas, TX 75254

SIGNATURE							Frank Ybarbo

TITLE:	See PCOs						Purchasing Agent

DATE: 								DATE:

MAIL SIGNED CHANGE ORDER TO:

Purchasing Agent, 200 S. McDonald St., Ste 230, McKinney, Texas 75069

Distribution to:  		Contract File	(  )	Contractor	(  )

Copies to:		Department	(  )	Auditor		(  )	Other			(  )